## Sheet1
| 2018-01-31 | 2018-02-07 | 2018-02-14 | 2018-02-21 | 2018-02-28 | 2018-03-07 | 2018-03-14 | 2018-02-12 | 2018-02-19 | 2018-02-26
Week: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Prototype PCB First routing
First routing checked/verified
Prototype PCB ordered
Prototype Assembled
Prototype tested
Production PCBs ordered
Production parts ordered
Kit assembly | [10 empty] | If we need to assemble 80 kits, we'll have around 1 month,
so that's 20 kits a week. At a low estimate of 1 hour per kit,
that’s 20 hours a week for a month
Divided among two people, that’s 10 hours a week for the month
Doable